## Task List
Task List
No. | Tasks | Owner | Priority | Start Date | Close Date | Process | Status
1 | Create Project Charter | Hưng | High | 2017-02-13 | 2017-02-14 | 90% | In Progress
2 | Create Project Charter | Hoàng | High | 2017-02-13 | 2017-02-14 | 90% | In Progress
3 | Level 2 Work Breakdown Structure | Hưng | Medium | 2017-02-15 | 2017-02-15 | 100% | Complete
4 | Level 2 Work Breakdown Structure | Khôi | Medium | 2017-02-15 | 2017-02-15 | 100% | Complete
5 | Create Slide for Presentation Phasre 1 | Mạnh | Low | 2017-02-16 | 2017-02-16 | 100% | Complete
6 | Create Slide for Presentation Phasre 1 | Sơn | Low | 2017-02-16 | 2017-02-16 | 100% | Complete
7 | Project Mangement Plan | Khôi | High |  |  | 0% | Not Started
8 | Find source code project and customize | Sơn | High |  |  | 20% | In Progress
9 | Create Activity and Attributes List | Khôi | Medium | 2017-02-21 | 2017-02-24 | 0% | In Progress
10 | Create a Precedence Network Diagram | Sơn | High | 2017-02-22 | 2017-02-24 | 0% | In Progress
11 | Estimate Resources and Duration for those Task | Hoàng | High | 2017-02-22 | 2017-02-24 | 100% | Complete
12 | Report the final schedule | Mạnh | Low | 2017-02-23 | 2017-02-24 | 0% | In Progress

## Sheet2
High | Complete
Medium | In Progress
Low | Not Started