## Task List
Task List
Tasks | Owner | Priority | Start Date | Close Date | Process | Status
Create Project Charter | Hưng | High | 2017-02-13 | 2017-02-14 | 70% | In Progress
Create Project Charter | Hoàng | High | 2017-02-13 | 2017-02-14 | 70% | In Progress
Level 2 Work Breakdown Structure | Hưng | Medium | 2017-02-15 | 2017-02-15 | 80% | In Progress
Level 2 Work Breakdown Structure | Khôi | Medium | 2017-02-15 | 2017-02-15 | 80% | In Progress
Create Slide for Presentation Phasre 1 | Mạnh | Low | 2017-02-16 | 2017-02-16 | 80% | In Progress
Create Slide for Presentation Phasre 1 | Sơn | Low | 2017-02-16 | 2017-02-16 | 80% | In Progress
Project Mangement Plan | Khôi | High |  |  | 0% | Not Started
Find source code project and customize | Sơn | High |  |  | 20% | In Progress
Create Slide for Presentation | Mạnh | Low |  |  | 0% | Not Started

## Sheet2
High | Complete
Medium | In Progress
Low | Not Started